## Test Info
THE DIG GAME ¦ TEST PLAN
PROJECT INFORMATION
Project Name | The Dig Game – Manual Testing | Game URL | https://louisdesimone.itch.io/the-dig-game
Project Type | Web Game | Browser | Chromium
Test Type | Manual Testing | Tester | Bartosz Sanecki
Test Level | System Testing | Start Date | 30 July 2026
Test Environment | Chromium browser - Desktop | End Date | 31 July 2026
Operating System | Fedora Linux 44
Test Status | completed
TEST SCOPE & APPROACH
Objective | Verify core gameplay mechanics, controls, collisions, terrain interaction and visual behavior.
In Scope | Movement and controls, collision detection, digging, physics and environment, gliding, camera, object interaction, UI/input where available, stability and edge cases.
Out of Scope | Multiplayer, security testing, performance benchmarking and features not available or not evaluated.
Approach | Manual functional testing, exploratory testing, visual testing and regression-oriented checks.
Tools | Chromium browser, spreadsheet documentation and Loom recordings supplied with the reported findings.
Limitations | Game build/version was not recorded. The test environment was Chromium browser on Fedora Linux 44. Some test scenarios depend on specific gameplay features or interactions being available.
TEST EXECUTION SUMMARY
Total test cases | 56 | Note | Summary counts are automatically updated based on the statuses in Test Cases. All test cases have been executed and their results documented.
PASS | 51
FAIL | 5
SKIPPED | 0
Total bug reports | 4

## Test Cases
THE DIG GAME ¦ TEST CASES
Test Case ID | Category | Test Scenario | Test Steps | Expected Result | Actual Result | Status | Bug ID | Notes
GAME-TC-001 | Movement & Controls | Move character forward | Press and hold the forward movement key. | Character moves forward as intended. | As expected. | PASS
GAME-TC-002 | Movement & Controls | Move character backward | Press and hold the backward movement key. | Character moves backward as intended. | As expected. | PASS
GAME-TC-003 | Movement & Controls | Move character left and right | Use the left and right movement controls. | Character moves in the intended directions. | As expected. | PASS
GAME-TC-004 | Movement & Controls | Stop character movement | Release all movement keys. | Character stops moving as expected. | As expected. | PASS
GAME-TC-005 | Movement & Controls | Change movement direction quickly | Alternate between opposite movement directions. | Character responds correctly without becoming stuck. | As expected. | PASS
GAME-TC-006 | Movement & Controls | Move while adjusting camera | Move the character while rotating the camera. | Movement remains controllable and consistent. | As expected. | PASS
GAME-TC-007 | Collision Detection | Fence collision | Approach a fence and attempt to move through it. | Character cannot pass through a solid fence. | Character can pass through a fence. | FAIL | GAME-BUG-004 | Reproduced.
GAME-TC-008 | Collision Detection | Walk along a fence | Move parallel to the fence. | Character follows the expected collision boundaries. | As expected. | PASS
GAME-TC-009 | Collision Detection | Approach fence from different angles | Attempt to pass through different parts of the fence. | Collision behavior remains consistent. | As expected. | PASS
GAME-TC-010 | Collision Detection | Terrain wall collision | Move the character horizontally toward a solid terrain wall and hold the movement key. | Character is blocked by the wall. | As expected. | PASS
GAME-TC-011 | Collision Detection | Collision near a corner | Approach a terrain corner from different directions. | Character does not unexpectedly clip through geometry. | As expected. | PASS
GAME-TC-012 | Collision Detection | Collision around a dug hole | Move around the edge of a dug hole. | Character interacts with terrain boundaries as intended. | As expected. | PASS
GAME-TC-013 | Digging Mechanics | Dig a soil block | Aim at soil and dig it with the left mouse button. | Targeted soil is removed as intended. | As expected. | PASS
GAME-TC-014 | Digging Mechanics | Dig a sand block | Aim at sand and dig it with the left mouse button. | Targeted sand is removed as intended. | As expected. | PASS
GAME-TC-015 | Digging Mechanics | Dig multiple adjacent blocks | Dig several neighboring blocks in sequence. | Each intended block is removed correctly. | As expected. | PASS
GAME-TC-016 | Digging Mechanics | Dig the same area repeatedly | Continue digging in an already modified area. | Repeated digging is handled without unexpected behavior. | As expected. | PASS
GAME-TC-017 | Digging Mechanics | Dig near a different material | Dig soil or sand next to another visible object or material. | Only intended targets are affected. | As expected. | PASS
GAME-TC-018 | Digging Mechanics | Dig while changing camera angle | Rotate the camera and continue digging. | Digging remains functional and targets the intended area. | As expected. | PASS
GAME-TC-019 | Digging Mechanics | Stop digging midway through an action | Release the left mouse button while digging. | Digging stops or completes according to game design. | As expected. | PASS
GAME-TC-020 | Digging Mechanics | Dig a narrow passage | Dig a narrow route through the terrain. | Terrain updates correctly and the passage remains accessible. | As expected. | PASS
GAME-TC-021 | Physics & Environment | Stones after surrounding soil is removed | Dig soil surrounding stones and observe them. | Stones behave according to the intended physics rules. | Stones remain floating after surrounding soil/sand is removed. | FAIL | GAME-BUG-001 | Reproduced.
GAME-TC-022 | Physics & Environment | Stones after surrounding sand is removed | Dig sand around stones and observe them. | Stones behave consistently with the intended physics rules. | Stones remain floating after surrounding soil/sand is removed. | FAIL | GAME-BUG-001 | Reproduced.
GAME-TC-023 | Physics & Environment | Objects near a newly created hole | Dig near visible objects and inspect their positions. | Objects remain in valid positions according to game rules. | As expected. | PASS
GAME-TC-024 | Physics & Environment | Environment after repeated digging | Dig several nearby blocks and inspect the result. | No unexpected gaps or visual inconsistencies appear. | As expected. | PASS
GAME-TC-025 | Physics & Environment | Observe unsupported objects | Remove surrounding material from an object that appears supported by it. | Object behavior matches intended game design. | As expected. | PASS
GAME-TC-026 | Physics & Environment | Inspect terrain after moving away and returning | Modify terrain, move away, then return to inspect it. | Terrain changes remain consistent during the session. | As expected. | PASS
GAME-TC-027 | Gliding Mechanics | Activate gliding | Double-press Space and hold it to activate gliding. | Gliding activates as intended. | As expected. | PASS
GAME-TC-028 | Gliding Mechanics | Maintain gliding | Continue holding Space during gliding. | Gliding remains active according to game rules. | As expected. | PASS
GAME-TC-029 | Gliding Mechanics | Change camera direction while gliding | Rotate the camera during gliding. | Camera movement does not unexpectedly interrupt gliding. | As expected. | PASS
GAME-TC-030 | Gliding Mechanics | Look downward while gliding | Activate gliding and point the camera down. | Glider remains visually stable. | Glider flickers or shifts position when the camera points downward. | FAIL | GAME-BUG-002 | Reproduced.
GAME-TC-031 | Gliding Mechanics | Look upward while gliding | Activate gliding and point the camera up. | Glider renders consistently. | As expected. | PASS
GAME-TC-032 | Gliding Mechanics | Observe glider during movement | Glide while changing direction. | Glider animation and position remain consistent with gameplay. | As expected. | PASS
GAME-TC-033 | Camera & Perspective | Rotate camera horizontally | Rotate the camera around the character. | Camera rotates as intended. | As expected. | PASS
GAME-TC-034 | Camera & Perspective | Rotate camera vertically | Look up and down using camera controls. | Camera responds correctly without unexpected artifacts. | As expected. | PASS
GAME-TC-035 | Camera & Perspective | Inspect objects from different angles | View nearby objects from multiple camera angles. | Objects remain visible and render consistently. | As expected. | PASS
GAME-TC-036 | Camera & Perspective | Camera near terrain walls | Move the camera close to a dug-hole wall. | Camera and nearby geometry render as intended. | As expected. | PASS
GAME-TC-037 | Camera & Perspective | Shovel clipping near a hole wall | Hold the shovel inside a hole and angle the camera toward the wall. | Shovel remains visible without unintended clipping. | Shovel partially disappears/clips into the wall at certain camera angles. | FAIL | GAME-BUG-003 | Reproduced.
GAME-TC-038 | Camera & Perspective | Rapid camera movement | Rotate the camera quickly in several directions. | Camera remains responsive without persistent visual artifacts. | As expected. | PASS
GAME-TC-039 | Visual Consistency | Object visibility during camera rotation | Rotate the camera around nearby objects. | Objects do not unexpectedly disappear. | As expected. | PASS
GAME-TC-040 | Visual Consistency | Visual consistency after digging | Dig several blocks and inspect the resulting terrain. | No unintended visual artifacts remain. | As expected. | PASS
GAME-TC-041 | Object Interaction | Hold shovel while moving | Move around the environment while holding the shovel. | Shovel remains attached to the character as intended. | As expected. | PASS
GAME-TC-042 | Object Interaction | Hold shovel while changing camera angle | Rotate the camera while the character holds the shovel. | Shovel remains correctly rendered. | As expected. | PASS
GAME-TC-043 | Object Interaction | Use shovel near terrain | Dig near a wall or the edge of a hole. | Shovel interaction behaves as intended. | As expected. | PASS
GAME-TC-044 | Object Interaction | Interact with nearby environment objects | Approach and interact with objects that support interaction. | Available interactions respond correctly. | As expected. | PASS
GAME-TC-045 | Object Interaction | Repeat an object interaction | Repeat the same available interaction several times. | Interaction remains consistent and does not become stuck. | As expected. | PASS
GAME-TC-046 | Game UI & Input Handling | Initial game loading | Open the game page and start the game. | Game loads and reaches a playable state. | As expected. | PASS
GAME-TC-047 | Game UI & Input Handling | Initial controls and instructions | Inspect the initial screen and any visible instructions. | Available instructions are readable and understandable. | As expected. | PASS
GAME-TC-048 | Game UI & Input Handling | Mouse input responsiveness | Use the mouse for supported gameplay interactions. | Mouse input is registered correctly. | As expected. | PASS
GAME-TC-049 | Game UI & Input Handling | Keyboard input responsiveness | Use supported keyboard controls individually. | Each control performs its intended action. | As expected. | PASS
GAME-TC-050 | Game UI & Input Handling | Repeated keyboard input | Press and release movement or action keys repeatedly. | Input continues to respond consistently. | As expected. | PASS
GAME-TC-051 | Stability & Edge Cases | Extended gameplay session | Play for an extended period while using normal mechanics. | Game remains responsive and playable. | As expected. | PASS
GAME-TC-052 | Stability & Edge Cases | Repeated digging and movement | Alternate between movement and digging repeatedly. | Gameplay remains functional without unexpected interruption. | As expected. | PASS
GAME-TC-053 | Stability & Edge Cases | Perform multiple actions in quick succession | Move, rotate the camera and dig in quick succession. | Inputs are handled without unexpected behavior. | As expected. | PASS
GAME-TC-054 | Stability & Edge Cases | Move into tight spaces | Navigate through narrow passages and near terrain boundaries. | Character movement follows intended collision rules. | As expected. | PASS
GAME-TC-055 | Stability & Edge Cases | Recover control after gliding | Stop gliding using the supported method. | Character returns to the expected movement state. | As expected. | PASS
GAME-TC-056 | Stability & Edge Cases | Return to a previously modified area | Dig an area, leave it and return. | Modified environment remains consistent with game design. | As expected. | PASS

## Bug Reports
THE DIG GAME ¦ BUG REPORTS
Bug ID | Title | Category | Environment | Preconditions | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Evidence
GAME-BUG-001 | Stones remain floating after surrounding soil/sand is dug | Physics / Environment | Chromium, Fedora Linux 44 | Stones are embedded in diggable soil or sand | 1. Launch the game. 2. Dig soil/sand using the left mouse button. 3. Uncover stones. 4. Observe the stones. | Stones behave according to intended physics/support rules after surrounding blocks are removed. | Stones remain suspended after surrounding soil/sand blocks are removed. | Major | High | Reported | ▶ Open evidence
GAME-BUG-002 | Glider flickers or shifts position when camera points down | Gliding / Rendering | Chromium, Fedora Linux 44 | Character can activate gliding | 1. Launch the game. 2. Double-press Space and hold it to glide. 3. Aim the camera downward. 4. Observe the glider. | Glider remains visually stable in its intended position. | Glider flickers and/or shifts position when the camera points downward. | Major | Medium | Reported | ▶ Open evidence
GAME-BUG-003 | Held shovel clips through dug-hole wall at certain camera angles | Camera / Clipping | Chromium, Fedora Linux 44 | Character holds a shovel and is inside a dug hole | 1. Launch the game. 2. Dig a hole. 3. Enter the hole holding the shovel. 4. Point the camera toward the wall. | Shovel is rendered consistently without unintended clipping. | Shovel partially disappears/clips into the hole wall at certain camera angles. | Minor | Medium | Reported | ▶ Open evidence
GAME-BUG-004 | Character can pass through a fence | Collision | Chromium, Fedora Linux 44 | Character is near a fence section | 1. Launch the game. 2. Approach the fence. 3. Attempt to move through it. 4. Observe collision behavior. | Fence collision prevents passage unless passage is intended by game design. | Character passes through the fence. | Major | High | Reported | ▶ Open evidence